## Instructions
Instructions
1) Add or Delete project roles as applicable to your project
2) Insert key tasks and deliverables by phase
3) For each task select the appropriate assignment based on the resources involvement in that particular task. (A legend is provided in cell A3)

## Consolidated RAM
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
Project Funding
Formulate Costs | S | P | S | S | S | I | P | S | I | S | S | S | S | S | I | I | S | S | I | A | I | I | I | I | I | I
Set Budget | S | P | S | S | S | I | P | I | I | S | I | I | I | I | I | I | I | I | I | A | I | I | I | I | I | I
Acquisition Planning | bar: S S
Develop work breakdown structure | A | A | P | S | S | I | S | I | I | P | S | S | S | S | I | S | S | I | I | A | I | I | I | I | I | I
Evaluate performance | P | P | S | S | S | I | I | S | I | I | P | S | P | S | I | P | S | S | I | I | I | I | I | I | I | I
Contracting | bar: A
Software Development Agreement | A | P | S | S | S | S | S | P | I | S | S | S | S | S | S | S | S | S | P | S | S | P | A | S | S | S
Time and Material Contract | A | P | P | S | I | I | S | P | I | P | S | P | P | I | I | I | I | I | P | S | S | P | A | S | S | S
Cost Reimbursable Contract | A | P | I | I | I | I | P | P | I | I | I | I | I | I | I | I | I | I | P | S | I | I | A | P | I | S
Requirements Analysis | bar: A A A
Business Requirement Analysis | A | P | P | I | P | P | P | P | I | P | I | I | I | I | I | I | I | I | I | I | I | I | I | P | I | I
Software & AI Requirement Analysis | A | P | I | P | I | I | I | I | I | I | P | I | P | I | I | I | I | I | I | I | I | I | I | I | I | I
System Design | bar: A A A
System Requirement Specification | A | P | S | S | S | S | S | P | I | S | A | A | S | A | S | S | S | S | I | S | I | I | S | S | I | I
Prototype | A | P | S | S | I | I | P | P | I | I | A | A | A | S | S | A | I | S | I | S | I | I | S | S | I | I
Data Management | A | A | I | I | I | I | I | P | I | I | A | A | A | S | S | A | I | S | I | S | I | I | S | S | I | I
System Development | bar: A A A
System Testing | S | S | S | P | S | I | I | I | I | I | A | A | P | A | I | P | S | S | I | I | I | I | I | I | I | I
Check Features | A | A | A | P | S | I | S | S | I | I | A | A | P | A | S | P | P | S | I | S | S | S | S | S | S | S
System Implementation | bar: S A
Deployment | A | P | A | I | A | S | S | A | I | I | S | A | P | P | A | A | S | S | S | A | I | I | I | S | S | S
Documentation | P | P | A | A | S | I | I | S | I | I | S | I | A | P | A | I | I | S | I | S | S | S | I | I | I | I
Resources
P
A
S
I

## Project Funding
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
Project Funding
Formulate costs | S | P | S | S | S | I | P | S | I | S | S | S | S | S | I | I | S | S | I | A | I | I | I | I | I | I
Set Budget | S | P | S | S | S | I | P | I | I | S | I | I | I | I | I | I | I | I | I | A | I | I | I | I | I | I
Get Approval | P | S | S | S | S | I | P | S | I | I | I | I | I | I | I | I | I | I | I | A | I | I | I | I | I | I
Resources
P
A
S
I

## Acquisition Planning
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
Acquisition Planning
Develop preliminary business case | S | P | S | S | P | S | S | S | I | S | S | S | I | I | I | I | I | I | I | A | I | I | I | I | I | I
Develop work breakdown structure | A | A | P | S | S | I | S | I | I | P | S | S | S | S | I | S | S | I | I | A | I | I | I | I | I | I
Communicate workload responsibilities | S | A | P | S | S | I | I | S | I | P | S | S | S | S | S | S | S | S | S | A | I | I | I | I | I | I
Identify requirements | A | A | P | S | S | I | A | S | S | S | S | A | S | I | I | I | I | I | I | A | I | I | I | I | I | I
Evaluate performance | P | P | S | S | S | I | I | S | I | I | P | S | P | S | I | P | S | S | I | I | I | I | I | I | I | I
Resources
P
A
S
I

## Contracting
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
Contracting
Software Development Agreement | A | P | S | S | S | S | S | P | I | S | S | S | S | S | S | S | S | S | P | S | S | P | A | S | S | S
Team Contract | A | P | S | S | P | P | S | P | S | S | S | S | S | S | S | S | S | S | P | S | S | S | A | S | S | P
Time and Material Contract | A | P | P | S | I | I | S | P | I | P | S | P | P | I | I | I | I | I | P | S | S | P | A | S | S | S
Fixed Price Contract | A | P | S | S | I | I | P | P | I | I | I | I | I | I | I | I | I | I | P | S | S | P | A | P | S | S
Customer Insception Rights | A | P | I | P | I | I | I | P | I | S | S | P | P | P | P | P | P | P | P | S | S | P | A | I | I | S
Intellectual Property Rights | A | P | I | I | I | I | I | P | I | I | I | I | P | P | P | I | I | S | P | S | I | I | A | I | I | P
Confidentiality | A | P | I | I | S | S | I | P | I | I | I | P | P | P | P | P | P | P | P | S | I | S | A | S | S | P
Cost Reimbursable Contract | A | P | I | I | I | I | P | P | I | I | I | I | I | I | I | I | I | I | P | S | I | I | A | P | I | S
Resources
P
A
S
I

## Requirements Analysis
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
Requirements Analysis
Existing System Requirement Analysis | I | P | I | P | I | I | I | I | I | I | P | I | P | I | I | I | I | I | I | I | I | I | I | I | I | I
Requirement Identification | I | P | P | P | P | P | P | P | I | P | P | I | P | I | I | I | I | I | I | I | I | I | I | P | I | I
Business Requirement Analysis | A | P | P | I | P | P | P | P | I | P | I | I | I | I | I | I | I | I | I | I | I | I | I | P | I | I
Software & AI Requirement Analysis | A | P | I | P | I | I | I | I | I | I | P | I | P | I | I | I | I | I | I | I | I | I | I | I | I | I
Finalising Requirement Analysis | A | P | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | P | I | I | P | A | I | I | I
Resources
P
A
S
I

## System Design
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
System Design
System Requirement Specification | A | P | S | S | S | S | S | P | I | S | A | A | S | A | S | S | S | S | I | S | I | I | S | S | I | I
Current System Analysis | S | P | S | S | S | S | S | S | S | S | A | A | S | A | S | S | S | S | I | S | I | I | S | S | I | I
Proposed System Analysis | S | P | S | S | S | S | S | S | S | S | A | A | S | A | S | S | S | S | I | S | I | I | S | S | I | I
Prototype | A | P | S | S | I | I | P | P | I | I | A | A | A | S | S | A | I | S | I | S | I | I | S | S | I | I
Design Flow Documentation | A | A | I | P | I | I | I | P | I | S | A | A | S | S | S | A | P | S | I | S | I | I | S | S | I | I
Data Management | A | A | I | I | I | I | I | P | I | I | A | A | A | S | S | A | I | S | I | S | I | I | S | S | I | I
Resources
P
A
S
I

## System Development
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
System Development
System Programming | S | S | S | S | S | I | I | I | I | I | S | A | P | A | I | I | S | S | I | I | I | I | I | I | I | I
Code Debugging | S | S | S | S | S | I | I | I | I | I | S | A | P | A | I | I | S | S | I | I | I | I | I | I | I | I
System Testing | S | S | S | P | S | I | I | I | I | I | A | A | P | A | I | P | S | S | I | I | I | I | I | I | I | I
Error Handling | S | S | S | P | S | I | I | I | I | I | A | A | P | A | I | A | S | S | I | I | I | I | I | I | I | I
Bug Resolve | S | S | S | P | S | I | I | I | I | I | I | A | P | A | I | A | S | S | I | I | I | I | I | I | I | I
Check Features | A | A | A | P | S | I | S | S | I | I | A | A | P | A | S | P | P | S | I | S | S | S | S | S | S | S
Resources
P
A
S
I

## System Implementation
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
System Implementation
System Deployment | A | P | A | I | A | S | S | A | I | I | S | A | P | P | A | A | S | S | S | A | I | I | I | S | S | S
Final Documentation | P | P | A | A | S | I | I | S | I | I | S | I | A | P | A | I | I | S | I | S | S | S | I | I | I | I
Resources
P
A
S
I