## Communications Guide
Communications Guide
Introduction | The Communication Plan contains communications activities and events for all internal and external stakeholders impacted by the project
Timing | The communications Plan should be developed during the Planning, Analysis and Design Phase of PMLC
Communication Plan | The Communications Plan outlines project key messages, branding and visual identity considerations, stakeholder needs, and planned communications events and activities.
Messaging | Key messages are the three or four most important statements about a project the team wishes to share with stakeholders. They should communicate both key facts and motive. Depending on the project, it may be important to both repeat some key messages over the life of the project, and introduce new messages as the project evolves.
Executive Staff | Recommend use External Relations and have Executive Sponsor Approval
Faculty | Recommend use External Relations and have approvals from Executive Sponsor, School Dean and/or Provost's Office
Staff | Recommend use External Relations and have approval from Executive Sponsor
Students | Recommend use External Relations and have approvals from Executive Sponsor and Provost's Office
External Stakeholders | Recommend use External Relations and have Executive Sponsor Approval
Messaging Medium | Some types of Communication have specific sign-off and requirements, see infomail as an example
Infomail Protocol and Guidelines | Provides an overview of protocols and guidelines as related to distribution of mass emails to University students, faculty and staff. Lead time, required sign-offs, and general information is in this guide
Branding and Visual Identity | All branding and visual identity must conform to the GW standards. Contact External Relations for guidelines.
Budget | ALL communications developed are constrained by the communications budget. As an example, If the project sponsor plans to communicate via printed materials using the USPS, the PM must contact external relations to get quotes for the printed material and related expenses. The lead time for this varies by the type of printed material.

## Communications Sample Entries
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Audience | Reviewer | Faculty / Staff / Student | Owner
1
| Name of the Communications Piece | Medium | Delivery Date | Frequency | Briefly describe the content of the communication piece | Person(s) who will receive the communication | Person(s) who will review and approve the communications piece | Faculty/Staff/Student | Person(s) responsible for document
| Examples: | Examples: | Examples: | Examples: | Examples: | Examples: | Examples: | Examples: | Examples:
| Reminder emails to Finance Staff | email | on-going | daily | design logo for iBuy Travel and Expense/Pcard | Finance Directors | External Relations | Faculty | External Relations - Joe
| Letter to Retirees re: benefit changes in 2012 | USPS Printed Letter | specify Date | weekly |  | All GW Employees | Excutive Sponsor | Student | Rebecca
| email to Executive Staff | 4 color Process Print |  | one-time |  | Retirees | Provost's Office | Staff | UWS (University Web Services)
| email to School of Business Faculty | Flyer |  | quarterly |  | Deans | Deans |  | IT Communications
| Memo to Faculty | meeting |  | yearly |  | Executive Staff | Executive Staff |  | FSS
|  | logo |  | bi-monthly |  | Faculty | Banner Steering Committee
|  | website |  |  |  | Students
|  | survey |  |  |  | Parents
|  | promotional piece |  |  |  | School of Nursing
|  | campus mail |  |  |  | VSTC Campus
|  | infomail |  |  |  | FB Campus
|  | GW Today |  |  |  | IT Help Desk
|  | Advertising |  |  |  | Banner Executive Committee
|  | phone |  |  |  | EAS Users
|  | training session |  |  |  | myGW Users
|  | memo |  |  |  | GWEB Users
meeting
ITSM Ticket

## Merit Project Communications
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Audience | Reviewer | Faculty / Staff | Owner
1 | Project Team Building | Virtual Meeting |  | At the early of the project | Introduction of team members and virtual team building activities | Customer Team Advisor | Customer Team Advisor | Staff | Jeyshalini Tevosha
2 | Project Team Communication | Virtual Meeting | Ongoing | Monthly | Weekly status meeting to discuss schedule, communications, actions, risks & issues | Project Team | Shivedhassen Balasingam | Staff | Jeyshalini Tevosha
3a | Executive Sponsor Communication | PPT | Ongoing | Monthly | Weekly status report to executive sponsors for overview of the project progress | Executive Sponsors | Jeyshalini Tevosha | Staff | Vishwareeta Vanoo
3b | Executive Sponsor Communication | Email | Ongoing | Monthly | Monthly executive overview of the project progress | Executive Sponsors | Jeyshalini Tevosha | Staff | Vishwareeta Vanoo
4 | Project status report | Virtual Meeting | Ongoing | Weekly | Review project statuses and discuss potential issues or delays | Poject Team | Shivedhassen Balasingam | Staff | Jeyshalini Tevosha
5 | Project review | Virtual Meeting | Ongoing | At milestones | Present project deliverables, gather feedback and discuss the upcoming steps | Project Team | Shivedhassen Balasingam | Staff | Previna Munuganan
6 | Post-mortem meeting | Virtual Meeting |  | At end of project | Discuss the blockers and obstacles throughout the project, and actionable takeaways | Poject Team | Vishwareeta vanoo | Staff | Jeyshalini Tevosha