## WBS with Gantt Chart - BLANK
Bank Loan Approval Prediction System
PROJECT TITLE | Bank Loan Approval Prediction System
PROJECT MANAGER | Jeyshalini Tevosha
COMPANY NAME | Gringotts Bank
DATE | 12/11/2020 | [5 empty] | PHASE ONE | [20 empty] | PHASE TWO | [20 empty] | PHASE THREE | [20 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F
WBS_01 | Specification
WBS_01_01 | System Requirement Specification | Shivedhassen | 2020-10-29 | 2020-11-01 | 3 | 100%
WBS_01_02 | Current System Analysis | Vishwareeta | 2020-11-02 | 2020-11-04 | 2 | 100%
WBS_01_03 | Proposed System Analysis | Previna | 2020-11-05 | 2020-11-10 | 5 | 100%
WBS_01_04 | Gantt Chart | Jeyshalini | 2020-11-11 | 2020-11-13 | 2 | 100%
WBS_02 | Development
WBS_02_01 | Prototype | Shivedhassen Vishwareeta | 2020-11-14 | 2020-11-16 | 2 | 10%
WBS_02_02 | Design Flow Documentation | Jeyshalini | 2020-11-17 | 2020-11-20 | 3 | 0%
WBS_02_03 | Data Management | Shivedhassen | 2020-11-14 | 2020-11-21 | 7 | 50%
WBS_02_04 | Programming | Jeyshalini Previna Shivedhassen Vishwareeta | 2020-11-22 | 2020-12-13 | 21 | 20%
WBS_02_05 | Debugging | Previna Vishwareeta | 2020-12-14 | 2020-12-18 | 4 | 0%
WBS_03 | Validation
WBS_03_01 | System Testing | Shivedhassen | 2020-12-19 | 2020-12-26 | 7 | 0%
WBS_01_02 | Error handling | Vishwareeta | 2020-12-27 | 2020-12-30 | 3 | 0%
WBS_03_03 | Bug Resolve | Previna | 2020-12-27 | 2020-12-30 | 3 | 0%
WBS_03_04 | Check Features | Jeyshalini Shivedhassen | 2020-12-27 | 2020-12-30 | 3 | 0%
WBS_03_05 | Client Verification | Jeyshalini | 2020-12-31 | 2021-01-05 | 5 | 0%
WBS_04 | Evolution
WBS_04_01 | Maintenance | Jeyshalini Vishwareeta | 2021-01-06 | 2021-01-10 | 4 | 0%
WBS_04_02 | Features update | Previna Shivedhassen | 2021-01-11 | 2021-01-15 | 4 | 0%